## High Level Road Map
v | Description | Resources | ETA | Long description
safe-for-production | Rally must be absolutelly safe to use against proudction clouds. | allocated | n/a | It means next: * Disaster cleanup. Even if server with running Rally was destroyed in the middle new instance of Rally on new service will know how to cleanup everything. * Rally deletes all own resources and doesn't delete anything else * Rally for most of benchmarks won't need admin user at all
scalability | Rally must have scalable engine and storage system | allocated | n/a | * Reports and Storing results should be scalable * Benchmarks should be able to run forever (millions of iterations) * Single task should be able to contain threads *
cloud-certification | The idea is to have 1 parametrized Rally input task that checks that everything works with required performance under expected load at expected scale. | allocated | n/a | Input Rally task will accept very high level arguments. E.g. amount of users/tenants/controllers/computes, specific flavors/images and purpose of the cloud (HPCC/DevTesting/PaaS/SaaS/IaaS/Hosting/...)
dataplane-testing | Testing VM/Disks perfromance, and running benchmark tools inisde the cloud | allocated | n/a | It means next: * Improve scenario output format * Improve reports to display this data * Implement base plugins that simplifes porting benchmarking tools to the cloud * Port existing benchmarking tools to Rally
better-reports | Various improvments in graphs to make them more understandable and self-sufficient | allocated | n/a | * More various graphs * Add benchmark description * Add infomration about enviorment
trends-analyze-reports | Analyzing results of the same benchmark(s) over the time | required | n/a | Such results like: Avg Duration, Amount of exceptions, SLA failures and rest can be used to build trends. So we can fetch tasks by tags and build such reports
results-comparison | Report with detailed comparions of two runs of Rally | required | n/a | This is very important and simplifes life for everybody that tries to tune configuration or code
framework-generalization | Rally should be common tool independet from OpenStack, that can benchmark anything including OpenStack | required | n/a | * All hardcoded to OpenStack places should be refactored * Restructurization of project to make it simple to split plugins from the framework * Splitting repo into 2: ** rally with framweork ** rally-openstack-plugins
plugin-managment-system | Rally should have plugin managment system e.g. http://npmjs.com | required | n/a | * Rally CLI for manage plugins (search/install/remove) * There should be a service for uploading/sharing/rating plugins
flexible-benchmark-engine | A lot of real life workflow can't be generated by current Rally benchmark engine | allocated | n/a | * Multi scenario load generation (required for real life testing) * Resturcturization of way how rally stores data * Better input task format: ** Strict order of execution ** Better benchmark naming & descriptions
ha-testing | Run in parallel descrutive scenario with normal scenario will allow us to check that HA actually works and fully auotmate HA testing | required | n/a | * Implement everything in flexible-benchmark-engine * Implement HA tests
as a service | Rally deamon that has HTTP API
api for raw data processing | Rally raw data processing API for custom report genration

## Long term road map
Name | Description | Prioirty | Status | Comment | requested by | Detailed design | Estimate | Assignee
production-ready-cleanup | Rally must cleanup all resources in any case. We have already pretty good mechanism with retries. But it doesn't work in 2 cases: rally or openstack crached. This effort is related to creating separated command "rally deployment cleanup" that will cleanup all resources even in case when we have new instance of rally This feature must be covered by functional tests as well | essential | in-progress |  | mcv services community |  |  | Chris St. Pierre | https://blueprints.launchpad.net/rally/+spec/production-ready-cleanup
task-verification-unification | Rally verifies input tasks before actually executing it. Task describe set of benchmark to run. Every benchmark consists from 1 Scenario, it's arguments, set of context, and runner. All this thing are pluging, every plugin has own argument. So it's essential to check that all arguments are valid and in case of mistakes write some human readble message. Currently mechanism for validating different type of plugins is different. This effort is to unify process of validation and use always "scneario" way via decorators. So one set of validators can be reused everywhere. | essential | in-progress |  |  |  |  | Boris Pavlovic
task-verification-levels | Currently Rally verification requires admin user, that will create tenant and user. So all validators will accept user and admin credentials and sometimes use them, sometimes not. This produce a lot of issues: admin is required, rally can't be used for non-OpenStack benchmarking, there is no way to make validation per tenant (in case of existing users), and so on and so on... | essential | in-progress |  |  |  |  | Boris Pavlovic
task-data-struct-refactor | The way that Rally store results is not perfect and doesn't allow us to implement various vital features. This effort will change DB model, results schema and benchamrk engine. As a result we will be able to implement such things like: 1) chunking results (scalability) 2) tracking running benchmark results (monitoring) | essential | in-progress | This is bloker for a lot of tasks requires my MOS teams |  |  |  | Boris Pavlovic | https://blueprints.launchpad.net/rally/+spec/refactor-db-schema
task-format-v2 | New task format that allows to specify multiscenario load | essential | in-progress |  | mos-scale community |  |  | Ilya Khudoshin | https://blueprints.launchpad.net/rally/+spec/new-task-format
multi-scenario-load | Ability to run different scenarios simultaneously. This feature is super hard cause it requires changes in all Rally reports, way how benchmark engine works, and input task format. So it will be delayed unit we answer on all questions that we have. | high | blocked | blocked by: task-data-struct-refactor document with design | mos-scale community | Discussion | n/a | Ilya Khudoshin
rally-scalable-engine | Rally is not able to run millions of iterations because, all information is store in RAM until benchmark process is finished. There are 2 ways to scale better engine. 1) chunk results 2) gzip data before storing to DB | high | blocked | blocked by: task-data-struct-refactor | mos-scale community |  | n/a | n/a
task-report-compare-2-results | Add abbility to generate HTML report that compares results of 2 tasks | high | pending |  | mos-scale community |  | Liberty | Alex Maretskiy | https://blueprints.launchpad.net/rally/+spec/report-compare
task-report-trends | Generate HTML report from results of N tasks (with same configuration) And shows how aggregated data changes. (Like avg duration of iterations, amount of failed iterations and so on) | high | pending |  | mos-scale community |  | Liberty | Alex Maretskiy | https://blueprints.launchpad.net/rally/+spec/trends-report
perf-job-multi-input-tasks | Be able to specify different types of input tasks for 1 single dsvm job. Like for gate-rally-dsvm-rally (job): rally_k3.yaml -> will run against keystone v3 deployment task rally_v3_ssl.yaml -> will run against keysotne v3 with ssl support rally_v2_existing_users -> will run against keystone v2 with already precreated users | high | in-progress | required for testing using existing users and ssl |  |  |  | Sergey skripnick
3party-master-perf-tracking | Running Rally periodically (2 times per day) against fresh master on the same hardware. That will allow us to collect information about how performance of master is changed during time. | high | blocked | blocked by: task-report-trends |  | Discussion | Liberty | Sergey Skripnick
vm-workloads-framework | Make a framework that simplifes integration of existing benchmarking tools to Rally. Basically what we need to do is to have mechanism (benchmark context) that prepare images (installs benchmark tool to it by running user specified script) and then trigger this tool (using user specified script) and standradtize output results Plus we should extend our task report to support more complex output format. Because now we are supporting {key: number} format only that doesn't work in many cases | high | in-progress |  | mos-scale mos-linux community | Discussion | Liberty | Pavel Boldin | https://blueprints.launchpad.net/rally/+spec/vm-workloads-framework
rally-plugin-package-manager | * Rally plugin CLI command (install, remove, list, search) * Rally package manager service (e.g. npm.js) | medium | pending
rally-verify-generialization | Add abbility to use rally verify for in-tree functional tests of all projects | medium | drafting |  | community | Discussion |  | Yair Fried Prasanth Anbalagan
load-gen-timeout | There is no timeout mechanism for iteration and timeout mechanism for constant runner is broken. After unfication of runner we should create some generic mechanism for timeouts | medium | in-progress |  |  |  |  | Roman Vasilets
rally-distributed-load-gen | Special load generator that creates distributed load using other load generators. This load generator should make next thing: 1) install rally on servers presented by specified "server provided" 2) run special rally agents 3) create benchmark context 4) send benchmark context and load specification to rally agents 5) trigger all agents 6) collect & store data to Rally DB 7) delete all servers with rally agents | medium | blocked | blocked by: load-gen-unfication task-data-struct-refactor rally-scalable-engine |  |  | n/a | n/a | https://blueprints.launchpad.net/rally/+spec/distributed-load-generation
rally-ramp-load-gen | Special load generator that creates increasing load using other load generators. It runs N times specified load generator with rising load | medium | blocked | blocked by: load-gen-unfication task-data-struct-refactor | mos-scale community |  | n/a | Roman Vasilets
persistance-context | Rally is creating benchmark context for every "benchmark" in task. So we are not able to create 1 context and use it in various task. This change adds new command "rally context" that will manage persistance context that can be used multiple times. Typical use case: 1) create N tenants M users L images in persistance context 2) run task with benchmark that list user images 3) change code / restart services 4) run one time same benchamrk to ensure that results are better Without this feature you'll need to create 2 times images. And if L is something like 10000 it can take quite long amount of time. | medium | blocked | blocked by: task-data-struct-refactor |  |  | n/a | Boris Pavlovic
multi-vm-workloads-framework | The same as in vm-workloads-framework but for distributed benchmark tools like iperf. Create (server/clinet) images in context using user scripts Boot N servers, M clinets and trigger tool, unify results | medium | blocked | blocked by: vm-workloads-framework | mos-scale mos-linux |  |  | Pavel Boldin
add-fuel-benchmarks | Add base set of Fule benchmark for "clusters", "enviorment" and so on | medium | blocked | blocked by: add-fuel-client |  |  | n/a | n/a
deploy-engine-fuel | Deploy engine based on Fuel based on fuel-dev-ops that will allow to have data driven testing of Fuel deploy mechanism | medium | pending |  |  |  | n/a | Sergey Skripnick
graceful-shutdown | We should be able to handle "ctrl+c" and have "rally task abort" cmd to stop running task gracefully. It means to do next step: 1) Send signal to load generator to stop 2) Mark task (and current task results) as aborted | medium | blocked | blocked by: task-data-struct-refactor |  |  | Kilo-3 | n/a | https://blueprints.launchpad.net/rally/+spec/graceful-shutdown
task-report-descriptions | Put information (docstring) from plugins in proper place of task report | medium | blocked | blocked by: task-data-struct-refactor |  |  | n/a | Alex Maretskiy
task-collect-request-id | Rally is using python clients to genereate request to OpenStack. Every request has own "request-id" we need the way to collect all requests that were done and store them to rally DB. This will simplify debuging | medium | pending |  |  |  | Kilo-3 | n/a
task-collect-all-http-request | Rally is using python clients to genereate request to OpenStack. Python clients are requesting OpenStack via HTTP, so it makes sense to collect and store all HTTP request. (Requested URL, response code, duration) | medium | in-progress |  |  |  | Kilo-3 | Andrey Kurilin
plugin-deprecation-mechanism | Rally is pluging deriven framework and sometimes we would like to rename/remove old pluings and keep backward compability for some amount of time (or in future for 2 releases). The goal of this effort is to add @depracated on any type of plugin and get warning if they are used. | medium | blocked | blocked by: switch-to-plugin-base |  |  | Kilo-2 | Boris Pavlovic
sample-decorator | Currently everybody who is making plugins for rally has to provide (manually written smaples in doc/samples/..) Which is not nice because: 1) it's hard to use in rally info command 2) it's unclear for new developers 3) it's hard to test 4) It's hard to manage 5) It's hard to automate generation of read-the-docs Much better approach is to add @sample decorator on top of plugin and unify this process for all types of plugins. And automate generation of /doc/samples/* | medium | in-progress |  |  |  | Kilo-2 | Oleg Anufriev
add-cloud-info-to-report | Put information about cloud to task report: 1) Create a list of information that can be collected about cloud 2) Understand what kinds of data we have (so we will have various types that will be used for displaying results) 3) Write code that will collect and store results with task 4) Write code that will display results in task report | medium | pending |  |  | Description
integration-osprofiler | OSprofiler allows us to trace request. So we can have a osprofiler context that will turn on/off profling. And during cleanup collect all traces from ceilometer or other backend and store to rally DB. After that extend rally task report to display traces as well. | low | blocked | blocked by: task-data-struct-refactor |  |  | Kilo-3 | n/a | https://blueprints.launchpad.net/rally/+spec/integrate-osprofiler
task-mutli-tag-support | This will allow us to list tasks by single tag from set as well generate reports based on tag | low | pending
100%-unit-coverage | cover evertyhing by unit tests | low | in-progress |  |  |  | n/a | Mike Dubov
integration-cbtool | CBtool is great tool for benchmarking VMs of various cloud system. So this thing allows end user to have simpler way to run cbtool against OpenStack clouds and get unified HTML report | low | blocked | blocked by: multi-vm-workloads-framework |  |  | n/a | n/a
integration-cloudroast | CloudRoast is alternative to Tempest. So it make sense to extend "rally verify" command and add support of it. | low | drafting | Started discussion with RackSpace team |  |  | n/a | n/a
rally-as-a-lib | Refactor current rally.orchestrator.api and make it as a rally lib interface. This lib interface will be common place for: 1) rally as a service deamon 2) rally python clinet (when it works in local mode) | low | in-progress |  |  |  | n/a | Mike Dubov
cmd-use-rally-lib-or-service | We should refactor rally.cmd code to use tiny wrapper that unifies usage of rally as a lib or as a service. That will help us to avoid duplication of code | low | blocked | blocked by: rally-as-a-lib rally-as-a-service |  |  | n/a | Alex Maretskiy
rally-as-a-service | Rally deamon that represents rally as a lib via REST | low | blocked | blocked by: rally-cmd-to-python-client rally-as-a-lib |  |  | n/a | Alex Maretskiy | https://blueprints.launchpad.net/rally/+spec/rally-as-a-service
rally-nested-atomic-actions | Allow to make nested atomic actions. Like if we are calling atomic inside atomic inside atomic it will get name: base_atomic->inner.atomic->even.deeper Basically in DB we should store next strucutre: { "base_atomic": {"started": ..., "finished": ..., "children": {"inner.atomic"}} } |  | pending
deploy-engine-packstack | Add new deploy engine based on packstack | wishlist | pending |  |  |  | n/a | n/a
deploy-engine-juju | Add new deploy engine based on juju | wishlist | pending |  |  |  | n/a | n/a
renew-deploy-code | There is a lot of usefull approaches in rally/benchmark that can be reused in rally-deploy code. Plus there is a lot of places that can be simplifed | wishlist | pending |  |  |  | n/a | n/a
task-status-advanced-reporting | We should show the status of task execution. Current running subtask, ETA for current subtask, % of done, ... | wishlist | pending |  |  |  | n/a | n/a
cmd-task-pause-resume | We should be able to pause task execution at any moment of time and resume |  | pending |  |  |  | n/a | n/a
register-task | The abbility to store inside Rally DB rally task templates and reuse them |  | pending |  |  |  | n/a | n/a
runner-based-on-sla-conditions |  |  | pending |  |  |  | n/a | n/a
task-score-system |  |  | pending |  |  |  | n/a | n/a
Note on D16: https://review.openstack.org/#/c/235910/ -rvasilets

## Release Schedule
Release Management Dev information -> |  |  |  | https://docs.google.com/document/d/1TX5zpYcTX8AXm-K_h1lzUNVCMvbRgsjUKU-dEYNWLY8/edit
Release | Expected date | Real date | Slip | Relative date | Relase notes | Status | Comments
0.0.1 | 2015-01-27 | 2015-01-27 | 0 | 932 days ago | https://rally.readthedocs.org/en/latest/release_notes/archive/v0.0.1.html | released | n/a
0.0.2 | 2015-03-12 | 2015-03-12 | 0 | 888 days ago | https://rally.readthedocs.org/en/latest/release_notes/archive/v0.0.2.html | released | n/a
0.0.3 | 2015-04-14 | 2015-04-14 | 0 | 855 days ago | https://rally.readthedocs.org/en/latest/release_notes/v0.0.3.html | released | n/a
0.0.4 | 2015-05-04 | 2015-05-14 | 10 | 835 days ago | https://rally.readthedocs.org/en/latest/release_notes/v0.0.4.html | released | *) may holidays *) 1 week ptl's vacation *) unstable infra gates
0.1.0 | 2015-09-25 | 2015-09-25 | 0 | 691 days ago | https://rally.readthedocs.org/en/latest/release_notes/v0.1.0.html | released
0.1.1 | 2015-10-09 | 2015-10-06 | -3 | 677 days ago | https://rally.readthedocs.org/en/latest/release_notes/v0.1.1.html | released
0.1.2 | 2015-10-19 | 2015-12-22 | 64 | 667 days ago | https://rally.readthedocs.org/en/latest/release_notes/v0.1.2.html | released
0.2.0 | 2016-01-11 | 2016-01-11 | 0 | 583 days ago | https://rally.readthedocs.org/en/latest/release_notes/v0.2.0.html | released
0.3.0 | 2016-02-16 | 2016-02-16 | 0 | 547 days ago | https://rally.readthedocs.org/en/latest/release_notes/v0.3.0.html | released
0.3.1 | 2016-02-19 | 2016-02-19 | 0 | 544 days ago | https://rally.readthedocs.org/en/latest/release_notes/v0.3.1.html | released
0.3.2 | 2016-03-04 | 2016-03-14 | 10 |  | https://rally.readthedocs.org/en/latest/release_notes/v0.3.2.html | released
0.3.3 | 2016-03-21 | 2016-03-24 |  |  | https://rally.readthedocs.org/en/latest/release_notes/v0.3.3.html | released
0.3.4 | 2016-04-04 |  |  |  |  | in-progress
0.x.y | 2016-04-11
Formulas:
Relative date = IF([Expected date]-TODAY() < 0, CONCATENATE(TODAY()-[Expected date], " days ago"), CONCATENATE("in ", [Expected date]-TODAY(), " days"))

## Implemented Kilo
Release | Name | Description | Prioirty | Comment | Assignee
kilo-1 | improve-plugins-doc-strings | All plugins should be covered by docstrings that will be used by rally report and rally info commands. This effort includes writing corresponding unit test | high |  | Mike Dubov
kilo-1 | context-obj-strcture-refactoring | Context object that is shared between all context and scenario currently has wrong structure. It allow to store only "user" specific resource and not "tenant" specific. This effort should make it possible to store user, tenant and global resources in context object. And cleanup current context plugins | high |  | Oleg Anufriev
kilo-1 | network-context | Rally should be able to create networks for created tenants. Otherwise we can't use VMTask.boot_run_command benchmak and assign networks to VM in case of Neutron deployment | high | mos-scale-request | Alex Maretskiy
kilo-1 | rally-cli-info | rally info is essential command that allows to find plugins and their description. It's already mostly implmented.. | medium |  | Mike Dubov
kilo-1 | 100%-functional-coverage | cover evertyhing by functional tests | low |  | Mike Dubov
kilo-2 | task-report-from-n-tasks | Add abbility to run commnad: rally task report with N uuids or N input files (with ouptut of rally task results) and generate single HTML report | high | mos-scale-request | Oleg Anufriev
kilo-2 | task-templates | Rally input tasks are hardcoded, which doesn't allow to have few "templates" with Golden Task to be able to verify and benchmark any cloud with any size. To fix this we are going to extend rally task start command so it will accept Jinja2 templates and arguments for it like: rally task start template.jinja2 --template-args "<yaml¦json>" or rally task start template.jinja2 --template-file FileWithTemplArgs.yaml This change includes as well improvemnts in gate-rally-dsvm-perf jobs. That will be extend to support template-file stuff. | high | mos-scale-request | Boris Pavlovic
kilo-2 | better-read-the-docs | Quality of Rally documentation is awful. We need to redesing it to make it simpler to start using/contributing to Rally | high | sales request | Mike Dubov
kilo-2 | releases | Rally is becoming more popular and popular. And even with quite stable master it's hard to create CI systems based on master. So releases will allow to simplify this process: 1) Standard way for making non backward compability changes: a) depraction b) one more relase c) delete depracted code 2) Release notes that will help user to understand what changed | high | mcv request | Boris Pavlovic
kilo-2 | support-postgres-db | Rally should support postgres backend. It includes next thing: 1) Gate job that tests unit tests against postgres 2) Fix all bugs related to postgres backend | high | mos-scale-request | Boris Pavlovic Sergey Skripnick
kilo-3 | add-mistral-base | * Add mistral client to Rally * Add first mistral benchmark to Rally (workbooks) * Add dsvm-murano-job * Add experimental job to rally queue | medium |  | Anastasia Kuznetsova Boris Pavlovic
kilo-3 | stop-loadgen-on-sla-failures | Abbility to stop exectuion of scenario if SLA checks failed. | high |  | Mike Dubov
kilo-3 | 3party-publish-docker-image | Update docker image on every merged patch to rally tree. Publish docker image for every Rally release | high |  | Sergey Skripnick
kilo-3 | 3party-functional-postgres-py27 | Functional job that checks that Rally works with postgresql backend | high | scale-request | Sergey Skripnick
kilo-3 | 3party-functional-postgres-py34 | Functional job that checks that Rally works with postgresql backend | medium |  | Sergey Skripnick
kilo-3 | remove-oslo-incubator-code | We are using oslo libs, part of oslo code is still in oslo-incubator. But this code is not used in Rally. It doesn't support py3 so we are removing it from Rally to avoid future issues | medium |  | Andrey Kurilin
kilo-3 | load-gen-unification | Various load generation are used to generete any kind of load that is required by user. What we saw is that optimal usage is common for all of them. Create N process (where N is count of CPU) use threads inside this processes to execute iteration and collect data. So we should implement common code for that and not copy paste. This effort will as well improve "constant" runner that uses now only processes | medium |  | Mike Dubov Boris Pavlovic
kilo-3 | refactor-constant-runner | Constant runner currently use process which doesn't allow to create enough big load. So we should create process equal to amount of cores and use threads to generate load | medium |  | Mike Dubov Boris Pavlovic
kilo-3 | py-34-support | Rally should work in python 34 well. This includes next steps: * fixing all py34 bugs and unit tests (done) * adding voting python34 job (done) * running functional tests in python34 as well (in progress not all bugs related to py34 are fixed) | medium |  | Andrey Kurilin, Arx Cruz Chen Li
kilo-3 | rally-throttling-load-gen | Special load generator that is throttling if cloud is starting dying | medium | RPS runner accepts max concurrency argument | Jesse Keating

## Implemented Liberty
Release | Name | Description | Prioirty | Comment | Assignee
liberty-1 | support-existing-users | Rally should be able to use existing users and tenants to generate load. This is essential for production clouds that are using LDAP, AD keystone backends with read only access. As well it allows to sandbox for benhmarking | essential | mcv services community | Boris Pavlovic
liberty-1 | functional-framework | Add "assertation" like in unit test to "base.scenario" and "base.context" This will allow us to write functional tests in Rally * Implement a FunctionalTestingMixin for base.Scenario & base.Context * Implement https://docs.python.org/2/library/unittest.html#assert-methods | high |  | Arx Cruz
liberty-1 | add-murano-base | * Add murano client * Add first murano benchmark to Rally * Add dsvm-murano-job (done) * Add experimental job to rally queue (done) | medium |  | Sergey Murashov Roman Vasilets Boris Pavlovic
liberty-1 | reogranize-plugins | Split framework and plugins, moving all plugins under separated tree | high |  | Yair
liberty-1 | fuel-base-benchmarks | * Add base for benchmarking fuel * Add some basic fuel benchmarks | medium |  | Alex Maretsky Oleh Anufriev
liberty-1 | 3party-mos-jobs | We should run Rally against MOS (juno/kilo/master) versions to ensure that Rally can be run against them and we don't break anything. As well this is multinode installation so we can test VM live migrate benchmark. | high |  | Sergey Skripnick
liberty-1 | add-fuel-client | Add to osclients fule client. This will allow us to benchmark | medium |  | Oleg Anufriev
liberty-2 | rally-task-results-in-subunit | Add new attribute --subunit to: * rally task detailed * rally task results | medium
liberty-3 | rally-task-abort | Command that allows to gracefully abort task execution | medium |  | Many devs...
liberty-3 | switch-to-plugin-base | Rally has various types of plugins. So part of duplication is duplicated across all of them. Such like: getting names, decoratros that sets up infomration about plugin, discovering, validation, getting info about plugin, depreation mechanism and so on. | essential |  | Boris Pavlovic
liberty-3 | seprated-rally-framework-plugin-base | Now rally/task/ contains only framework and rally/plugins/ only plugins | essential |  | Boris Pavlovic
liberty-3 | rally-plugins-to-docs | Extend sphinx to generate page that contains infomration about all plugins | low |  | Boris Pavlovic
liberty-3 | rally-reports-scalable | Reports are build using additive algorithms |  |  | Alex Maretsky
liberty-3 | verify-tempest-conf-generation | Rally generates Proper Tempest configuration |  |  | Yaroslav Lobankov
liberty-3 | veriy-import-tempest-results | Rally verify can import already existing tempest results, for future work with results, like HTML/CSV reports or comapring 2 runs